Capstone Project Report

Report 2 – Project Management Plan

– Ho Chi Minh City, October 2025 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	5

1.3 Project Risks	5

2. Management Approach	6

2.1 Project Process	6

2.2 Quality Management	6

2.3 Training Plan	7

3. Project Deliverables	8

4. Responsibility Assignments	8

5. Project Communications	9

6. Configuration Management	9

6.1 Document Management	9

6.2 Source Code Management	9

6.3 Tools & Infrastructures	10

I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 28/10/2025 | A | Duong Minh Nhat | Adding document |
| 10/11/2025 | M | Duong Minh Nhat | Updating document |
| 01/12/2025 | M | Duong Minh Nhat | Reviewing and updating document |

*A - Added M - Modified D - Deleted

II. Project Management Plan

1. Overview

1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Web Application for Admin |  | 22 |
| 1.1 | FE-01: Login/Logout | Simple | 2 |
| 1.2 | FE-02: Manage personal profile | Simple | 2 |
| 1.3 | FE-03: Manage user account | Medium | 4 |
| 1.4 | FE-04: Manage program (assign courses) | Medium | 5 |
| 1.5 | FE-05: Manage course | Simple | 3 |
| 1.6 | FE-07: Manage class (assign instructor) | Medium | 6 |
| 2 | Web Application for Simulation Manager |  | 32 |
| 2.1 | FE-08 & FE-09: Auth & Profile | Simple | 2 |
| 2.2 | FE-10: Manage simulation component | Complex | 6 |
| 2.3 | FE-11: Manage simulation action | Medium | 5 |
| 2.4 | FE-12: Manage simulation practice | Complex | 7 |
| 2.5 | FE-13: Manage practice step | Complex | 6 |
| 2.6 | FE-14: Manage practice warning | Medium | 3 |
| 2.7 | FE-15: Manage simulation timeslot | Medium | 3 |
| 3 | Web Application for Instructor |  | 28 |
| 3.1 | FE-16 & FE-17: Auth & Profile | Simple | 2 |
| 3.2 | FE-18: Manage class member | Simple | 2 |
| 3.3 | FE-19 & FE-20: Manage sections & materials | Medium | 6 |
| 3.4 | FE-21: Manage quiz (assign to section) | Medium | 6 |
| 3.5 | FE-22: View & assign practices | Simple | 3 |
| 3.6 | FE-23: View results & provide feedback | Medium | 5 |
| 3.7 | FE-24: View overall performance & grading | Medium | 4 |
| 4 | Web Application for Trainee |  | 24 |
| 4.1 | FE-25 & FE-26: Auth & Profile | Simple | 2 |
| 4.2 | FE-27: View programs/enrollment | Medium | 4 |
| 4.3 | FE-28 & FE-29: View syllabus & materials | Simple | 3 |
| 4.4 | FE-30: Quiz attempt & history | Complex | 8 |
| 4.5 | FE-31: View practice results | Simple | 3 |
| 4.6 | System Integration (API & Database) | Complex | 4 |
| 5 | 3D Simulation Application (Desktop) |  | 45 |
| 5.1 | SI-01: Login/Logout (API Integration) | Simple | 3 |
| 5.2 | SI-02: List practices & selection | Medium | 4 |
| 5.3 | SI-03 & SI-04: Guides, Settings & Steps UI | Medium | 6 |
| 5.4 | SI-05: Simulation Physics (Lift, Rotate, Inspect) | Complex | 15 |
| 5.5 | SI-06: Error detection & warning system | Complex | 10 |
| 5.6 | SI-07: Result calculation & submission | Medium | 7 |
|  | Total Estimated Effort (man-days) |  | 151 |

1.2 Project Objectives

| # | Testing Stage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- |
| 1 | Reviewing | 40 | 35% |  |
| 4 | System Test | 45 | 40% |  |
| 5 | Acceptance Test | 20 | 25% |  |

1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Technology risk: to target available tools and framework for project overall requirements | High | Medium | Do research and testing of different technical solutions before developing main features. |
| 2 | Requirement misunderstanding risk: to correctly specify each requirement based on real-world scenarios and best-practice solution | High | High | Verify requirements with evaluation from realistic data or references, have reviews with stakeholders. |

2. Management Approach

2.1 Project Process

The project will be executed using the Agile software development methodology, specifically the Scrum framework. This approach allows the team to adapt to changes quickly, deliver incremental value, and ensure continuous feedback throughout the development lifecycle.

Sprints: The development timeline is divided into 2-week Sprints. Each sprint focuses on delivering a specific set of features (from the Product Backlog) that results in a potentially shippable product increment.

Key Roles:

- Product Owner (Leader): Responsible for defining the product vision, managing the Product Backlog, and prioritizing features based on stakeholder value.

- Scrum Master (Rotational/Assigned): Ensures the team adheres to Scrum practices, removes obstacles (blockers), and facilitates meetings.

- Development Team (All Members): Cross-functional members responsible for designing, coding, testing, and integrating the software.

- Scrum Ceremonies:

- Sprint Planning (Day 1 of Sprint): The team selects items from the Product Backlog to work on during the sprint and breaks them down into tasks.

- Daily Stand-up (15 mins): A brief daily meeting where members report what they did yesterday, what they will do today, and any blockers they are facing.

- Sprint Review (Last Day of Sprint): The team demonstrates the completed work to supervisors/stakeholders to gather feedback.

- Sprint Retrospective (After Review): The team discusses what went well, what didn't, and how to improve processes for the next sprint.

2.2 Quality Management

To ensure the "Learner Management and 3D Simulation System" meets high-quality standards and functional requirements, the team will implement the following quality assurance measures:

Defect Prevention:

- Coding Standards: The team will adhere to standard C# (.NET) and JavaScript (React) coding conventions to ensure code readability and maintainability.

- Static Code Analysis: Tools will be used in the IDE (Visual Studio/VS Code) to catch syntax errors and potential bugs early during development.

- Clear Requirements: All User Stories must have defined "Acceptance Criteria" before development begins to prevent misunderstanding.

- Reviewing:

- Peer Code Reviews: All code changes must be submitted via Pull Requests (PR) on GitHub. At least one other team member must review the code for logic errors, style violations, and potential performance issues before it is merged into the main or develop branch.

- Document Reviews: Project documents (SRS, SDD) are reviewed by the Supervisor and team members to ensure consistency and completeness.

- Testing Strategy:

- Unit Testing: Developers are responsible for writing unit tests for critical business logic, particularly for the API (Backend) services and complex Simulation algorithms.

- Integration Testing: Verifying that different modules work together correctly.

  - Web App: Testing communication between the React Frontend and .NET Backend APIs.

  - Simulation: Testing the data exchange between the Unity Desktop App and the Backend Server (e.g., login, score submission).

- System Testing (Functional Testing): The team will execute manual test cases based on the SRS to verify that the system functions as a whole and meets all user requirements (e.g., An instructor assigning a quiz, a trainee completing a simulation).

- User Acceptance Testing (UAT): Conducted near the end of the project (or Sprint Reviews) where the Supervisors/Instructors test the system to confirm it meets their business needs.

- Bug Tracking:

- Defects found during testing will be logged in GitHub Issues or the project management tool (Jira/Excel) with a priority level (Critical, High, Medium, Low) and assigned to a developer for fixing.

2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Unity | All members | 2 weeks | Mandatory |
| Blender | All members | 2 weeks | Mandatory |
| ASP.NET | All members | 2 weeks | Mandatory |
| React | All members | 2 weeks | Mandatory |
| Github | All members | 2 weeks | Mandatory |

3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Project Introduction document | 24/10/2025 | Overall project description |
| 2 | Project Management document | 26/10/2025 | Project estimation and management approach |
| 3 | SRS document | 05/11/2025 | Software Requirement Specification |
| 4 | Software Design Document | 15/11/2025 | System Design, Detailed Design, Database |
| 5 | Software Testing Document | 05/12/2025 | Test Document, Test Report |
| 6 | Final Report Document | 10/12/2025 | Project Final Report |
| 7 | Web Application | 10/12/2025 | Project Web Application Product |
| 8 | 3D Simulation Application | 10/12/2025 | Project Desktop Application Product |
| 9 | Source Code Repository | 10/12/2025 | Complete source code for all subsystems. |
| 10 | Project Package | 10/12/2025 | Final codes & documents |

4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | NhatDNSE182236 | DucDTSE180110 | KhoiPDSE170462 | QuangLNSE170415 |
| --- | --- | --- | --- | --- |
| Project Introduction document | D | R | R | R |
| Project Management document | D | R | R | R |
| SRS Document | S | R | D | D |
| Software Design Document | D | S | D | R |
| Software Testing Document | R | S | R | D |
| Final Report Document | D | R | S | S |
| Web Application | D | R | D | D |
| 3D Simulation Application | R | D | R | S |
| Source Code Repository | D | R | R | R |
| Project Package | R | D | D | D |

5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Working with supervisor | Supervisors (Mr. Ngo Dang Ha An and Mr. Pham Thanh Tri) and team members | • Review Project requirement and documentation • Demonstrate Major features • Evaluate technologies, solutions and result | 1 times per week | Face to face, Google Meet |
| Working in team | Team members | • Specify tasks, reviews and opinions • Ask for member’s help • Report working status to leader | Always | Discord, Zalo, Face to face |

6. Configuration Management

6.1 Document Management

- Using Google Drive to save documentations:

- Using Google Sheet to take notes:

- Using Draw.io to save design and diagrams:

6.2 Source Code Management

- Using Github to store source code:

  - Backend API Repository:

  - Frontend Web App Repository:

  - Simulation Desktop App Repository:

- Follow these rules when using Git:

  - Commit convention:

    - Commit code with syntax: git commit -m "type: what-commit-does"

    - Types of commits include:

      - feat: new feature

      - fix: handle bug

      - config: change related to config file

      - docs: changes related to config file documentation

      - test: adding testing code

  - Pull request convention:

    - Attach a link to the task on Notion in the description of the pull request

    - Do not push code directly to main/master branch. Let’s create a new branch for every new task

    - Tag the leader for code review

6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Unity (Simulator), Blender (Modeling), .NET (Backend), React (frontend) |
| Database | Microsoft SQL Server |
| IDEs/Editors | Visual Studio, Visual Studio Code |
| Diagramming | Draw.io, Lucidchart |
| Documentation | Ms Office, Google Docs/Sheets |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Microsoft Azure |
| Project management | Jira, Google Sheets |